Goodyear House Private Events

Action Plan: Roles, Responsibilities & Next Steps

Source: Meeting notes — Sean, AJ, Aaron, Lauren

# Summary

The objective is to convert GYH private events from a reactive, lightly tracked function into a measurable sales pipeline with a clean handoff between marketing, sales response, pricing, and execution. Sequencing matters: brochure and competitive intel feed the sales pitch; tracked phone/email and Tripleseat hygiene feed pipeline data; data feeds pricing logic; pricing logic feeds the AI-assisted proposal tool. Skip the order and the later pieces stall.

## Strategic Priorities (in order)

- Fix the front door — inquiry response time, tracked phone number, updated brochure, automated touches that feel natural.

- Sharpen the pitch — competitor reviews, refreshed brochure (incl. wedding section), Chiefs cross-sell.

- Get clean data — Toast, Tripleseat, OpenTable pulls so we understand demand, ADR, cover trends before automating pricing.

- Build the pricing engine — rules-based, then AI-assisted proposal output.

- Scale the system — replicate across Folia, Chiefs, OTKC after GYH is dialed in.

## Open Questions Flagged for AJ

- AI vendor for traffic-driving: Fred and Briana to surface options as they have an AI tool that may work for initial communications that drive conversions.

- Tripleseat capabilities: Can it (a) send SMS, (b) attach PDFs/links to inquiry auto-replies, (c) accept inquiries via portal/text/email/phone in one funnel? Lauren to confirm first.

- Dedicated events phone number: needs to be trackable (call recording + source attribution) and forwardable to Lauren. Decide on platform — CallRail, OpenPhone, or similar — before procuring.

- Competitor set: Wedgewood in plaza midwood, Supperland, La Belle Helene, Oak Steakhouse Charleston, Steak 48 serve different segments. Recommend splitting wedding-focused vs. fine-dining-private-room teardowns so Lauren isn't comparing apples to oranges. Crystal/Lauren to pull down private events brochures from each and go through process saving each communication

# Roles & Responsibilities

Each workstream below is mapped to a single owner. Where multiple people are listed, the first name is accountable; others support.

| Role / Person | Owns | Responsibilities |
| --- | --- | --- |
| AJ | Strategic oversight, vendor decisions, voicemail drop content | Approves brochure, vendor selection (AI/phone/CRM tools); helps approve voicemail drop with Jack setting up if needed; final sign-off on pricing rules |
| Sean | Cross-portfolio strategy | Aligns GYH playbook with broader BOH portfolio rollout (Folia, Chiefs, OTKC, Beckworth) |
| Lauren (Events Mgr) | Sales execution & content owner | Owns inquiry response, competitor research, brochure copy input, Tripleseat workflow, email/SMS sequence content, referral pricing intel; Gets event photo/video sourcing |
| Aaron (GYH GM) | Menu & on-property execution | Owns menu insert, on-property event coordination, kitchen/FOH coordination for events |
| Crystal | Design | Brochure design and production (after Lauren delivers copy + competitor inputs) |
| VA | Listings, outreach, system entry | Wedding-group registrations, convention outreach lists, Tripleseat data entry, automated outreach to date-night tags, Folia/Chiefs/OTKC replication support |
| Fred / Briana | AI vendor sourcing | Identify and vet AI vendor candidates for traffic generation |
| Jack | Production support | Assists AJ with voicemail drop recording |
| Heather | Referral channel | Provides referral pricing/markup intel; Lauren to debrief; |

# Workstream 1: Inquiry Response & Front Door

Goal: first-touch within 15 minutes during business hours; full multi-channel coverage; every inquiry tracked to source.

### Current Process (as-is)

- Client submits inquiry form.

- Automated email sent (currently cost-focused, not sales-focused).

- Manual follow-up depending on staff availability.

### Target Process (to-be)

- Inquiry hits via form, dedicated phone line, text, email, or Tripleseat guest portal — all routed to one queue.

- Auto-reply email fires immediately: sales-led copy, links to updated brochure (PDF), photo/video Dropbox, Instagram. No pricing in initial reply.

- Within 3 hours: voicemail drop from Lauren (pre-recorded with AJ/Jack’s help if needed).

- Within 24 hours: live callback attempt by Lauren.

- Day 2: automated SMS — 'we reached out by voicemail yesterday, happy to answer questions or hold a date.'

- Day 5: second automated touch if no response (email, not SMS — avoid spam triggers).

- Day 10: manual review by Lauren; mark as lost with reason code or continue nurture.

### Action Items

| Action | Owner | Deadline | Notes / Dependencies |
| --- | --- | --- | --- |
| Procure dedicated events phone number; ensure call tracking + forwarding to Lauren when on-shift | Lauren | Week 1 | Confirm platform (CallRail / OpenPhone / similar); must integrate with Tripleseat or at minimum log to CRM |
| Confirm Tripleseat capabilities: SMS send, PDF/link attach on auto-reply, multi-channel inquiry intake | Lauren | Week 1 | Direct ask to Tripleseat support; document what's possible vs. what needs workaround |
| Rewrite initial auto-reply email — sales tone, brochure link, photo/video link, IG link; remove cost talk | Lauren | Week 2 | Draft to AJ for review; run through Claude for sales tweaks |
| Record Lauren voicemail drop (~30 sec, warm, ends with callback CTA) | AJ + Jack + Lauren | Week 2 | Test deliverability before deploying to live inquiries |
| Build automated SMS day-2 sequence in Tripleseat (or alternative) | Lauren + VA | Week 3 | Depends on Tripleseat SMS confirmation; otherwise use Twilio/Klaviyo |
| Build day-5 email follow-up automation | Lauren | Week 3 | Separate template; do not duplicate auto-reply |
| Set up Dropbox of event photos/videos; outreach to wedding photographers, planners for usable assets | Lauren | Week 2 | Needs release/usage permission from photographers |
| Add response-time SLA to Lauren's KPIs: 15 min business hours, 2 hr off-hours | future | Week 2 | Pair with weekly pipeline review |

# Workstream 2: Brochure & Marketing Collateral

Goal: brochure that reflects current GYH positioning, includes a wedding-specific section benchmarked against actual wedding venues, and cross-sells Chiefs for casual/cocktail-style events.

### Action Items

| Action | Owner | Deadline | Notes / Dependencies |
| --- | --- | --- | --- |
| Pull competitor brochures: Wedgewood, Supperland, La Belle Helene, Oak Steakhouse, Steak 48 | Lauren | Week 1 | Go through their inquiry process online; cold call where useful; collect materials |
| Source wedding-venue brochures specifically (separate from above) | Lauren | Week 1 | Wedgewood is the closest wedding-venue comp; supplement with 2–3 dedicated wedding venues in market |
| Annotate competitor materials: what we like, what we'd skip, gaps GYH can own | Lauren | Week 2 | Use Claude to suggest verbiage refinements |
| Draft new GYH brochure copy incl. wedding section + Chiefs cross-sell page | Lauren + AJ | Week 3 | Crystal to design after copy locked |
| Design final brochure | Crystal | Week 4 | Print-ready PDF + web-optimized PDF |
| Add brochure to GYH website (events page) | Crystal + VA | Week 5 | Updates required to current events landing page |
| Add menu insert promoting private events | Aaron | Week 4 | Time to coincide with next menu reprint |
| Register GYH on all relevant Charlotte wedding Facebook groups & venue listing sites | VA | Week 3 | Lauren to provide approved bio/photos; VA to compile master list of groups + sites |
| Compile Charlotte convention/conference list; outreach campaign to event planners | VA | Week 4 | Outreach template from Lauren; track responses in Tripleseat or spreadsheet |

# Workstream 3: Data Integration & Pricing Logic

Goal: replace gut-feel pricing with rules-based pricing informed by historical Toast, Tripleseat, and OpenTable data. AI-assisted proposal generation is the end state — but only after the data foundation is clean.

### Phase A — Pull historical data (Weeks 1–3)

- Toast sales data via Toast IQ — by month, by daypart, by service type — to establish baseline revenue we'd need to displace for a buyout to be profitable

- Tripleseat API pull of past events — type, size, revenue, F&B avg, room rental, lead time

- OpenTable API pull of historical covers — most accurate guest count benchmark by date

### Phase B — Build pricing rules document (Weeks 3–4)

Documented rules that any coordinator (or AI) can apply. Inputs:

- Buyout vs. semi-private vs. private room

- Guest count (drives menu tier and labor model)

- Day of week + time (peak vs. off-peak)

- Season / weather sensitivity (outdoor space implications)

- Trending sales for the requested date — what would we displace?

- Confidence the party will exceed minimum (drop minimum, take the booking)

- Lead time to event date (close-in dates priced differently than 6-month out)

### Phase C — AI-assisted proposal tool (Weeks 5–8)

Lauren or VA enters inquiry details; tool outputs proposal range with menu suggestions and pricing tiers. Built on top of the pricing rules doc — not freestanding.

### Action Items

| Action | Owner | Deadline | Notes / Dependencies |
| --- | --- | --- | --- |
| Toast IQ deep-dive: 12-month historical revenue by date/daypart for GYH | AJ + Aaron | Week 1 | Identifies revenue we'd displace with buyouts; flags peak/trough dates |
| Tripleseat API extract: all events 2024 + YTD 2025 with full data fields | VA + Lauren | Week 2 | Clean into spreadsheet; identify gaps in historical data quality |
| OpenTable API extract: covers by day for 24 months | VA | Week 2 | Cross-reference with Toast for cover-vs-revenue patterns |
| Draft pricing rules PDF with all inputs above | AJ + Lauren | Week 4 | Include decision tree; Claude to assist with structure |
| Get Heather's referral pricing intel — what her clients mark up, channel norms | Lauren | Week 2 | Find older lead; ask directly |
| Build prototype AI proposal tool (Claude project or similar) | AJ + Lauren | Week 6 | Don't build before pricing rules locked |
| Test proposal tool against 10 historical inquiries; measure variance vs. what was actually quoted/booked | Lauren | Week 8 | Calibration step; tune rules before going live |

# Workstream 4: Sales Process Discipline

Goal: every Lauren email, sales conversation, and proposal goes through a quality check. Capture institutional knowledge for replication across portfolio.

### Action Items

| Action | Owner | Deadline | Notes / Dependencies |
| --- | --- | --- | --- |
| All outbound emails from Lauren / GYH events run through Claude for sales tone & tweaks | Lauren | Ongoing — start Week 1 | Set up Claude project with brand voice + recent successful emails as context |
| Document GYH event night flow end-to-end — set, service, breakdown | Lauren + Aaron | Week 3 | Speak into Claude / record voice notes; add photo tour of typical event night |
| Setup automated outreach to 'date night' guest tag list (re-engage existing fans for private events) | VA | Week 4 | Segment from Tripleseat / Toast guest data; soft pitch, not a hard sell |
| Weekly pipeline review — Lauren + AJ — pipeline, win/loss reasons, response-time adherence | Lauren + AJ | Recurring — start Week 2 | 30 min standing meeting |

# Workstream 5: Portfolio Replication

Once GYH is dialed in (target: end of Week 8), apply the same playbook to the rest of the portfolio.

### Action Items

| Action | Owner | Deadline | Notes / Dependencies |
| --- | --- | --- | --- |
| Replicate process at Folia | VA + Sean | Weeks 9–12 | Same brochure / inquiry / pricing rules framework, concept-specific copy |
| Replicate process at Chiefs | VA + Sean | Weeks 9–12 | Casual/cocktail positioning; cross-sell linkage with GYH wedding section |
| Replicate process at OTKC | VA + Sean | Weeks 13–16 | Concept-specific package design needed |
| Beckworth pre-opening private events plan | AJ + Sean | Pre-opening | Build into opening playbook — don't bolt on after launch |

# Consolidated Timeline

| Period | Milestones |
| --- | --- |
| Week 1 | Phone number procured; Tripleseat capabilities confirmed; Toast IQ pull begins; competitor brochures collected |
| Week 2 | Auto-reply rewrite; voicemail drop recorded; Tripleseat + OpenTable API extracts; Heather pricing debrief; weekly pipeline review begins |
| Week 3 | Brochure copy drafted; SMS sequence built; date-night and convention list outreach begins; event flow documented |
| Week 4 | Brochure designed; pricing rules PDF drafted; menu insert; convention outreach |
| Week 5 | Brochure on website; auto-flows live and monitored |
| Week 6 | AI proposal tool prototype |
| Week 8 | AI proposal tool calibrated against historical events; GYH playbook locked |
| Weeks 9–12 | Folia + Chiefs rollout |
| Weeks 13–16 | OTKC rollout; Beckworth planning |

# Items Requiring AJ Decision

These were flagged in notes but lack a clear owner or path. Resolving these unblocks downstream work.

- AI vendor for traffic generation: define scope (paid acquisition vs. SEO vs. outbound) before Fred/Briana shortlist.

- Phone tracking platform: CallRail vs. OpenPhone vs. Tripleseat-native — pick one before Week 1.

- Tripleseat continuation vs. alternative: if Tripleseat can't do SMS + multi-channel intake + PDF attach cleanly, evaluate switching cost vs. workaround now, not in 6 months.

- Wedding venue competitive set: confirm we're treating wedding rehearsal/reception as a distinct segment from corporate/social — affects brochure, packaging, and outbound.

- Lauren's KPIs and comp structure: response-time SLA, conversion targets, and any event-sales commission need to be documented and aligned before pipeline reviews start.